## Monthly Timetable
Monthly Finance Reporting Timetable 2017/18
Year | 2017
Service |  |  | Reporting deadline dates 2017/18
| Task Lead | Reporting period |  |  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Year-end
|  | Calendar month |  |  | May | June | July | August | Sept | Oct | Nov | Dec | Jan | Feb | March | April
|  | First Day of Month |  |  | 2017-05-01 | 2017-06-01 | 2017-07-01 | 2017-08-01 | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-01-01 | 2018-02-01 | 2018-03-01
|  | First Working Day of Month |  |  | 2017-05-02 | 2017-06-01 | 2017-07-03 | 2017-08-01 | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2017-12-01 | 2018-01-02 | 2018-02-01 | 2018-03-01
|  | Key Tasks | Working day | Day Diff | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Date | Comments/ Dependencies
Budgets | P1 | Revenue Funds Transfer Form (RFT) | -11 | -11 | 2017-04-12 | 2017-05-16 | 2017-06-16 | 2017-07-17 | 2017-08-16 | 2017-09-15 | 2017-10-17 | 2017-11-16 | 2017-12-13 | 2018-01-17 | 2018-02-14 | Year-end timetable
| P1 | Upload budget virements as requested | -1 | -1 | 2017-04-28 | 2017-05-31 | 2017-06-30 | 2017-07-31 | 2017-08-31 | 2017-09-29 | 2017-10-31 | 2017-11-30 | 2017-12-29 | 2018-01-31 | 2018-02-28
| P1 | Post and action monthly IATs | 1 | 0 | 2017-05-02 | 2017-06-01 | 2017-07-03 | 2017-08-01 | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2017-12-01 | 2018-01-02 | 2018-02-01 | 2018-03-01
| P1 | Reconcile monthly Budget Book | 10 | 9 | 2017-05-15 | 2017-06-14 | 2017-07-14 | 2017-08-14 | 2017-09-14 | 2017-10-13 | 2017-11-14 | 2017-12-14 | 2018-01-15 | 2018-02-14 | 2018-03-14
Payroll | P2 | Monthly payroll interface | -4 | -4 | 2017-04-25 | 2017-05-25 | 2017-06-27 | 2017-07-26 | 2017-08-25 | 2017-09-26 | 2017-10-26 | 2017-11-27 | 2017-12-22 | 2018-01-26 | 2018-02-23
| P1 | Payroll Adjustment Journal | -3 | -3 | 2017-04-26 | 2017-05-26 | 2017-06-28 | 2017-07-27 | 2017-08-29 | 2017-09-27 | 2017-10-27 | 2017-11-28 | 2017-12-27 | 2018-01-29 | 2018-02-26
Receivables / Payables | P2 | Unallocated receipts to be cleared | -5 | -5 | 2017-04-24 | 2017-05-24 | 2017-06-26 | 2017-07-25 | 2017-08-24 | 2017-09-25 | 2017-10-25 | 2017-11-24 | 2017-12-21 | 2018-01-25 | 2018-02-22
| P1 | Raise invoice requests for income | -3 | -3 | 2017-04-26 | 2017-05-26 | 2017-06-28 | 2017-07-27 | 2017-08-29 | 2017-09-27 | 2017-10-27 | 2017-11-28 | 2017-12-27 | 2018-01-29 | 2018-02-26
| ALL | Raise any sales orders requested | -2 | -2 | 2017-04-27 | 2017-05-30 | 2017-06-29 | 2017-07-28 | 2017-08-30 | 2017-09-28 | 2017-10-30 | 2017-11-29 | 2017-12-28 | 2018-01-30 | 2018-02-27
|  | Ledger Close/Rollover 4pm | -1 | -1 | 2017-04-28 | 2017-05-31 | 2017-06-30 | 2017-07-31 | 2017-08-31 | 2017-09-29 | 2017-10-31 | 2017-11-30 | 2017-12-29 | 2018-01-31 | 2018-02-28
Non PO | IR | Email Budget Holders to Code & Approve Invoices | -3 | -3 | 2017-04-26 | 2017-05-26 | 2017-06-28 | 2017-07-27 | 2017-08-29 | 2017-09-27 | 2017-10-27 | 2017-11-28 | 2017-12-27 | 2018-01-29 | 2018-02-26
| ALL | Code non-po items | 1 | 0 | 2017-05-02 | 2017-06-01 | 2017-07-03 | 2017-08-01 | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2017-12-01 | 2018-01-02 | 2018-02-01 | 2018-03-01
| P2 | Prior Year Auto PO- Review and Recode | 1 | 0 | 2017-05-02 | 2017-06-01 | 2017-07-03 | 2017-08-01 | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2017-12-01 | 2018-01-02 | 2018-02-01 | 2018-03-01
| P5 | Prior Year Paid Invoices - Review and Recode | 1 | 0 | 2017-05-02 | 2017-06-01 | 2017-07-03 | 2017-08-01 | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2017-12-01 | 2018-01-02 | 2018-02-01 | 2018-03-01
Acute | P3 | Monthly SLAM file saved and reviewed | -5 | -5 | 2017-04-24 | 2017-05-24 | 2017-06-26 | 2017-07-25 | 2017-08-24 | 2017-09-25 | 2017-10-25 | 2017-11-24 | 2017-12-21 | 2018-01-25 | 2018-02-22
| P3 | Claims and challenges template sign off | -3 | -3 | 2017-04-26 | 2017-05-26 | 2017-06-28 | 2017-07-27 | 2017-08-29 | 2017-09-27 | 2017-10-27 | 2017-11-28 | 2017-12-27 | 2018-01-29 | 2018-02-26
| P3 | Overall Acute report complete | 5 | 4 | 2017-05-08 | 2017-06-07 | 2017-07-07 | 2017-08-07 | 2017-09-07 | 2017-10-06 | 2017-11-07 | 2017-12-07 | 2018-01-08 | 2018-02-07 | 2018-03-07
| P3 | Final ledger input completed | 6 | 5 | 2017-05-09 | 2017-06-08 | 2017-07-10 | 2017-08-08 | 2017-09-08 | 2017-10-09 | 2017-11-08 | 2017-12-08 | 2018-01-09 | 2018-02-08 | 2018-03-08
| P3 | Draft Board report slides completed | 9 | 8 | 2017-05-12 | 2017-06-13 | 2017-07-13 | 2017-08-11 | 2017-09-13 | 2017-10-12 | 2017-11-13 | 2017-12-13 | 2018-01-12 | 2018-02-13 | 2018-03-13
Finance Summary | P1 | Set up Monthly Finance Summary 2pm | 4 | 3 | 2017-05-05 | 2017-06-06 | 2017-07-06 | 2017-08-04 | 2017-09-06 | 2017-10-05 | 2017-11-06 | 2017-12-06 | 2018-01-05 | 2018-02-06 | 2018-03-06
| ALL | Update Narrative 3pm | 4 | 3 | 2017-05-05 | 2017-06-06 | 2017-07-06 | 2017-08-04 | 2017-09-06 | 2017-10-05 | 2017-11-06 | 2017-12-06 | 2018-01-05 | 2018-02-06 | 2018-03-06
| RC/MR | HOF Review 3pm | 5 | 4 | 2017-05-08 | 2017-06-07 | 2017-07-07 | 2017-08-07 | 2017-09-07 | 2017-10-06 | 2017-11-07 | 2017-12-07 | 2018-01-08 | 2018-02-07 | 2018-03-07
Final Position | P1/P5 | Agree additional adjustments | 5 | 4 | 2017-05-08 | 2017-06-07 | 2017-07-07 | 2017-08-07 | 2017-09-07 | 2017-10-06 | 2017-11-07 | 2017-12-07 | 2018-01-08 | 2018-02-07 | 2018-03-07
| P2 | Final review of I&E & B/S coding | 7 | 6 | 2017-05-10 | 2017-06-09 | 2017-07-11 | 2017-08-09 | 2017-09-11 | 2017-10-10 | 2017-11-09 | 2017-12-11 | 2018-01-10 | 2018-02-09 | 2018-03-09
| P4 | Final Live report run 1pm | 7 | 6 | 2017-05-10 | 2017-06-09 | 2017-07-11 | 2017-08-09 | 2017-09-11 | 2017-10-10 | 2017-11-09 | 2017-12-11 | 2018-01-10 | 2018-02-09 | 2018-03-09
|  | Ledger Hard Close 4pm | 7 | 6 | 2017-05-10 | 2017-06-09 | 2017-07-11 | 2017-08-09 | 2017-09-11 | 2017-10-10 | 2017-11-09 | 2017-12-11 | 2018-01-10 | 2018-02-09 | 2018-03-09
Internal Reporting | P1/P5 | Risks & Opportunities Schedule | 6 | 5 | 2017-05-09 | 2017-06-08 | 2017-07-10 | 2017-08-08 | 2017-09-08 | 2017-10-09 | 2017-11-08 | 2017-12-08 | 2018-01-09 | 2018-02-08 | 2018-03-08
| P1/P5 | Budget holders meetings | 10 | 9 | 2017-05-15 | 2017-06-14 | 2017-07-14 | 2017-08-14 | 2017-09-14 | 2017-10-13 | 2017-11-14 | 2017-12-14 | 2018-01-15 | 2018-02-14 | 2018-03-14
| P1/P5 | Finance review with senior management team | 15 | 14 | 2017-05-22 | 2017-06-21 | 2017-07-21 | 2017-08-21 | 2017-09-21 | 2017-10-20 | 2017-11-21 | 2017-12-21 | 2018-01-22 | 2018-02-21 | 2018-03-21
External Reporting | P3 | Financial Position (Surplus/Deficit) return | 7 | 6 | 2017-05-10 | 2017-06-09 | 2017-07-11 | 2017-08-09 | 2017-09-11 | 2017-10-10 | 2017-11-09 | 2017-12-11 | 2018-01-10 | 2018-02-09 | 2018-03-09
| P3 | Non-ISFE return | 7 | 6 | 2017-05-10 | 2017-06-09 | 2017-07-11 | 2017-08-09 | 2017-09-11 | 2017-10-10 | 2017-11-09 | 2017-12-11 | 2018-01-10 | 2018-02-09 | 2018-03-09
Balance Sheet | P2 | Prior Year Control Reconcilaition | 6 | 5 | 2017-05-09 | 2017-06-08 | 2017-07-10 | 2017-08-08 | 2017-09-08 | 2017-10-09 | 2017-11-08 | 2017-12-08 | 2018-01-09 | 2018-02-08 | 2018-03-08
| P2 | Complete VAT returns | 16 | 15 | 2017-05-23 | 2017-06-22 | 2017-07-24 | 2017-08-22 | 2017-09-22 | 2017-10-23 | 2017-11-22 | 2017-12-22 | 2018-01-23 | 2018-02-22 | 2018-03-22
| P2 | SBS Control Account reconciliations prepared | 18 | 17 | 2017-05-25 | 2017-06-26 | 2017-07-26 | 2017-08-24 | 2017-09-26 | 2017-10-25 | 2017-11-24 | 2017-12-28 | 2018-01-25 | 2018-02-26 | 2018-03-26
| P2 | All Control Account reconciliations reviewed | 20 | 19 | 2017-05-30 | 2017-06-28 | 2017-07-28 | 2017-08-29 | 2017-09-28 | 2017-10-27 | 2017-11-28 | 2018-01-02 | 2018-01-29 | 2018-02-28 | 2018-03-28
VAT | P2 | Vat returns review | 18 | 17 | 2017-05-25 | 2017-06-26 | 2017-07-26 | 2017-08-24 | 2017-09-26 | 2017-10-25 | 2017-11-24 | 2017-12-28 | 2018-01-25 | 2018-02-26 | 2018-03-26
| P2 | Submit VAT return on line | 20 | 19 | 2017-05-30 | 2017-06-28 | 2017-07-28 | 2017-08-29 | 2017-09-28 | 2017-10-27 | 2017-11-28 | 2018-01-02 | 2018-01-29 | 2018-02-28 | 2018-03-28

## Holidays
2017-01-02 | Monday | New Year’s Day (substitute day)
2017-04-14 | Friday | Good Friday
2017-04-17 | Monday | Easter Monday
2017-05-01 | Monday | Early May bank holiday
2017-05-29 | Monday | Spring bank holiday
2017-08-28 | Monday | Summer bank holiday
2017-12-25 | Monday | Christmas Day
2017-12-26 | Tuesday | Boxing Day
2017-01-01 | Monday | New Year’s Day
2017-03-30 | Friday | Good Friday
2017-04-02 | Monday | Easter Monday
2017-05-07 | Monday | Early May bank holiday
2017-05-28 | Monday | Spring bank holiday
2017-08-27 | Monday | Summer bank holiday
2017-12-25 | Tuesday | Christmas Day
2017-12-26 | Wednesday | Boxing Day
2018-01-01 | Monday | New Year's Day
2018-03-30 | Friday | Good Friday
2018-04-02 | Monday | Easter Monday
2018-05-07 | Monday | Early May Bank Holiday (May Day)
2018-05-28 | Monday | Spring Bank Holiday
2017-08-27 | Monday | August Bank Holiday
2018-12-25 | Tuesday | Christmas Day
2018-12-26 | Wednesday | Boxing Day